## Sheet1
Team member
Paolo | Yevhen | Woldy | Oliver | Ke
Product backlog
Story ID | Story title | Card | Story points | Sprint | Status | Conversitaion | Confirmation
Paolo
BK-1 | Functionality | As a participant, I want to see the qustions for survey | 8 | 1 | done | This will allow a participant to see the questions list for a survey | 1. a participant can see the survery question list
BK-2 | Functionality | As a participant, I want to answer the qustions for survey | 7 | 2 | In progress | Having this ability will ensure the participant to answer all the quesitons for the survey | 1. A participant can get a token by email 2. A participant can answer the questions for a survey by accessing the link with a token
BK-3 | Functionality | As an administrator, I want to regiester in the system | 9 | 2 | In progress | This will allow an administrator to register in the poll planet system | 1. An adminitrator can sign up In the system 2. A registered administrator can login the system.
BK-4 | Functionality | As an administrator, I want to login into the system | 5 | 2 | In progress | Having this ability will ensure the administrator to login into the system | 1. The registered administrator can pass the authorization 2. The administrator can login into the system
BK-5 | Functionality | As an administrator, I want to update my profile | 7 | 2 | In progress | This will allow an administrator to edit his/her profile | 1. The reistered administrator can update his/her profile
BK-6 | Functionality | As an administrator, I want to delete my profile | 3 | 2 | In progress | This will allow an administrator to delete his/her profile | 1. The reistered administrator can delete his/her profile from the system
BK-7 | Functionality | As an administrator, I want to maintain questions for survery | 9 | 2 | In progress | This will allow an administrator to maintain questions for a survey | 1. The registered administrator can add questoins for surveys 2. The registered administrator can update the questions for surverys. 3. The registered administrator can delete questions for surverys.
BK-8 | Functionality | As an administrator, I want to see the analysis about the survey | 5 | 2 | In progress | This will allow an administrator to review the survey analysis report | 1.The registered administrator can view the survey result.
BK-9 | Functionality | As an administrator, I want to export/print the survey results | 3 | 3 | In progress | This will allow an administrator to export/print the survey analysis report | 1.The registered administrator can export/print the survey result.
Sprint 1 Backlog
Story ID | Task ID | Task title | Task description |  | Status
Paolo
BK-1 | BK-1.1 | DB design | Determine the db structure |  | done
BK-2 | BK-1.2 | Use case design | Determine the use cases |  | done
BK-1 | BK-1.3 | Home page with header navigation | Create a UI page for poll planet system with header navigation |  | done
BK-1 | BK-1.4 | View a survey questons list | View the survey question list for a participant |  | done
BK-1 | BK-1.5 | Retrive a survey questions list API | Provide an get questions list API for front-end and return the questions data from database |  | done
BK-1 | BK-1.6 | Create database and test data in db | create a sql file for database table structures and insert sql for testing data |  | done
Sprint 2 Backlog