## Sheet1
Team member
Paolo | Yevhen | Woldy | Oliver | Ke
Sprint 1 Backlog
Story ID | Task ID | Task title | Task description |  | Ideal Hours | Status | Comments
Paolo
BK-1 | BK-1.1 | DB design | Determine the db structure |  | 1.5 hrs | done
BK-1 | BK-1.2 | Use case design | Determine the use cases |  | 1.5 hrs | done
BK-1 | BK-1.3 | Home page with header navigation | Create a UI page for poll planet system with header navigation |  | 5 hrs | done
BK-1 | BK-1.4 | View a survey questons list | View the survey question list for a participant |  | 4 hrs | done
BK-1 | BK-1.5 | Retrive a survey questions list API | Provide an get questions list API for front-end and return the questions data from database |  | 2 hrs | done
BK-1 | BK-1.6 | Create database and test data in db | create a sql file for database table structures and insert sql for testing data |  | 4 hrs | done