## Sheet1
Sprint 2 Backlog
Story ID | Task ID | Task title | Task description | Ideal Hours | Status | Comments
BK-2 | BK-2.1 | Administrator sign up page | Administrator form page and input fields validation | 5 hrs | in progress
BK-2 | BK-2.2 | Administrator call API | Submit administrator form data to call API and send data to back end | 1.5 hrs | in progress
BK-2 | BK-2.3 | Restore registration form data to db | provide register api for administrator, receive the form data and insert into database | 2 hrs | in progress
BK-2 | BK-2.4 | Wireframes | Create and modify wireframes | 4 hrs | in progress
BK-2 | BK-2.5 | Diagrams | Provide detailed diagrams (Database,use-case) | 3 hrs | in progress
BK-2 | BK-2.6