## Sheet1
Team member
Paolo | Yevhen | Woldy | Oliver | Ke
Activities Table
Date | Who |  |  |  |  | type of activity | No. of hours spent | Purpose | Output
| Paolo | Yevhen | Woly | Oliver | Ke
Milestone 1
Milestone 2
Sprint 1
2023-07-11 | 1 | 1 | 1 | 1 | 1 | meeting in class | 15 | discuss system structure | documents for DB diagram, use-case diagram, blog etc.
2023-07-11 | 1 | 0 | 0 | 0 | 0 | DB diagram work | 4
2023-07-11 | 1 | 0 | 0 | 0 | 0 | UML diagram work | 2
2023-07-11 | 0 | 0 | 1 | 0 | 0 | Wire frame work | 4 |  | wire frame draft
2023-07-11 | 0 | 1 | 0 | 1 | 0 | Logo work | 4 | designing
2023-07-13 | 1 | 0 | 0 | 1 | 0 | DB script work | 4 | creating DB | .sql script
2023-07-13 | 1 | 1 | 1 | 1 | 1 | meeting in class | 15 | Verifying diagrams/wireframes | Wirefram
2023-07-13 | 0 | 0 | 0 | 0 | 1 | server side of DB | 2 | build server
2023-07-14 | 1 | 1 | 1 | 1 | 1 | face to face meeting | 35 | DB and HTML/CSS work
2023-07-14 | 1 | 0 | 0 | 0 | 0 | DB work | 2 | connecting DB to server
2023-07-15 | 0 | 0 | 0 | 0 | 1 | Server work | 2 | connecting DB to server
2023-07-16 | 1 | 0 | 1 | 0 | 0 | Troubleshooting | 4 | DB connection issues with front-end for Olivier | resolved
Sprint 2
2023-07-17 | 0 | 1 | 0 | 0 | 0 | frontend | 4 | create sign-in/sign-up pages
2023-07-17 | 0 | 0 | 1 | 0 | 0 | frontend | 4 | create contact-us pages
2023-07-18 | 1 | 0 | 0 | 1 | 0 | database and server | 4 | added routes for surveys and user-registration | more routes are functioning
2023-07-18 | 0 | 1 | 0 | 0 | 0 | frontend | 3 | create main survays page and update survay page
2023-07-18 | 0 | 1 | 0 | 0 | 0 | frontend and server | 6 | store answers into DB middleware for corn policy
2023-07-19 | 0 | 1 | 0 | 0 | 0 | frontend | 5 | login validation, cookies, connect to DB(get users)
2023-07-19 | 1 | 0 | 0 | 0 | 0 | db diagram | 2 | added more tables and relationships to db diagram
2023-07-19 | 1 | 0 | 0 | 1 | 0 | server routes | 2 | added more routes to admin APIs
2023-07-20 | 1 | 0 | 0 | 0 | 0 | server routes | 4 | added bcrypt and checks for registration and login
2023-07-24 | 1 | 0 | 0 | 0 | 0 | created openAPI doc | 3 | created .yml file for API documentation