## Sheet1
Sprint 3 Backlog
Story ID | Task ID | Task title | Task description | Ideal Hours | Status | Comments
BK-3 | BK-3.1 | Multi tenant (Backend) | add more routes and authentication for multiple tenants exclusively accessing their surveys | 3 hrs | in progress
BK-3 | BK-3.2 | Admin authentification (backend) | add authentication for administrator data to call API and send data to back end | 3 hrs | in progress
BK-3 | BK-3.3 | Multi-question types capability (backend) | add capability in server and database to support multiple question types (boolean, multi-select etc.) | 2 hrs | in progress
BK-3 | BK-3.4 | admin setup for analytics | add feature for administrator to access analytics page with search functionality | 4 hrs | in progress
BK-3 | BK-3.5 | Survey pages for admin | administrator's access to view/edit existing surveys with basic search functionality | 3 hrs | in progress
BK-3 | BK-3.6 | Multi-tenant (front-end) | setup front-end to accomodate multiple tenants/organizations. they would have customized logos and styling with the same page-layout and functionality. | 2 hrs | in progress
BK-3 | BK-3.7 | Multi-question types capability (frontend) | add capability in fontend-app to support multiple question types (boolean, multi-select etc.) on "Submit" | 2 hrs | in progress
BK-3 | BK-3-8 | GCP | deploy database to GCP | 1.5 hrs | Not started yet
BK-3 | BK-3.9 | Admin dashboard | Setup Dashboard to allow admin to manage, manipulate and export data |  | Not started yet
BK-3 | BK-3.10 | Data Visualsation | From the dashboard allow admins to have various data visualisation options: Tables,charts, etc.... |  | Not started yet
BK-3 | BK-3.11 | Blog feature | Blog section to display articles that will display creative ways to use PollsPlanet in everyday life |  | Not started yet