## Sheet1
Team member
Paolo | Yevhen | Woldy | Oliver | Ke
Activities Table
Date | Who |  |  |  |  | type of activity | No. of hours spent | Purpose | Output
| Paolo | Yevhen | Woly | Oliver | Ke
Milestone 1
2023-07-11 | 1 | 1 | 1 | 1 | 1 | meeting in class | 3 | discuss system structure | documents for DB diagram, use-case diagram, blog etc.
2023-07-11 | 1 | 0 | 0 | 0 | 0 | DB diagram work | 4
2023-07-11 | 1 | 0 | 0 | 0 | 0 | UML diagram work | 2
2023-07-11 | 0 | 0 | 1 | 0 | 0 | Wire frame work | 4 |  | wire frame draft
2023-07-11 | 0 | 1 | 0 | 1 | 0 | Logo work | 2 | designing
2023-07-13 | 1 | 0 | 0 | 1 | 0 | DB script work | 2 | creating DB | .sql script
2023-07-13 | 1 | 1 | 1 | 1 | 1 | meeting in class | 3 | Verifying diagrams/wireframes | Wirefram
2023-07-13 | 0 | 0 | 0 | 0 | 1 | server side of DB |  | build server
2023-07-14 | 1 | 1 | 1 | 1 | 1 | face to face meeting | 7 | DB and HTML/CSS work
2023-07-14 | 1 | 0 | 0 | 0 | 0 | DB work | 1 | connecting DB to server
2023-07-15 | 0 | 0 | 0 | 0 | 1 | Server work | 2 | connecting DB to server
2023-07-16 | 1 | 0 | 1 | 0 | 0 | Troubleshooting | 2 | DB connection issues with front-end for Olivier | resolved
Milestone 2
Sprint 1